## Project
Pass/Go
Fail
On Hold
WorkFlow Project: | Release of Stop Payment
Business Line (BL): | Deposit Services
Business Line Owner: | Leigh Anne Rozell
Business Lines to Test
BA Analyst: | Alex Morris
WorkFlow Analyst (WFA): | Ross Staples
WorkFlow Version: | 1.1

## WFA Testing
| WorkFlow Project: | Release of Stop Payment | Testing Date: | 2024-09-03
| Business Line Testing: | WorkFlow Analyst | Final Results:
| Test Plan Designed By: |  | Test Plan Executed By: | Ross Staples
Scenario #1: | Release of Stop Payment: Non-post = yes and Deposit Services Approve Release
Test Case #: | Test Scenario: | Expected Results: | Actual Results: | Status: | Notes:
S1-1 | Start Workflow from queue | First manual activity will auto open | First MA opened | Pass/Go
S1-2 | 1st MA: Enter Account Number | Enter account number to pull back customer information | Account number entered | Pass/Go | Account# 700310808
S1-3 | 2nd MA: Enter Stop Payment Info | Enter the stop payment info: Select Customer, How SP was requested, Date SP was placed, Amount, Present on Non-post. | The SP info was entered | Pass/Go | I selected the customer from the drop down and entered $300 in the amount to find a specific stop payment
S1-4 | 3rd MA: Select Stop to Release | Select the desired stop payment from the drop down | The correct stop payment was in the drop down | Pass/Go
S1-5 | Email Deposit Services for Review | Email Deposit Services when Non-post = yes | Email was successfully sent with link that opens queue | Pass/Go
S1-6 | 4th MA: Review for Deposit Services | MA for Deposit Services to view SP info, add comments, and approve/deny release | Comment has been added and release approved | Pass/Go
S1-7 | 5th MA: Confimation of SP Release | Confirmation MA opens in queue to notifify requestor that SP was released | Confirmation successful | Pass/Go
S1-8 | Document Filed to Synergy | Document files successfully to synergy | Fields and Indexes succesfully filled | Pass/Go | Account was a checking account so it was placed in Stop Payments - DDA in synergy
S1-9 | Confirm Stop was removed from customer account | Stop Payment should no longer be on customer account | Stop has been removed from account | Pass/Go
S1-10
S1-11
S1-12
S1-13
S1-14
S1-15
S1-16
S1-17
S1-18
S1-19
S1-20
S1-21
S1-22
Scenario #2: | Release of Stop Payment: Non-Post = yes and Deposit Services Deny Release
Test Case #: | Test Scenario: | Expected Results: | Actual Results: | Status: | Notes:
S2-1 | Start Workflow from queue | First manual activity will auto open | First MA opened | Pass/Go
S2-2 | 1st MA: Enter Account Number | Enter account number to pull back customer information | Account number entered | Pass/Go | Account# 144564327
S2-3 | 2nd MA: Enter Stop Payment Info | Enter the stop payment info: Select Customer, How SP was requested, Date SP was placed, Amount, Present on Non-post. | The SP info was entered | Pass/Go | No amount was entered
S2-4 | 3rd MA: Select Stop to Release | Select the desired stop payment from the drop down | The correct stop payment was in the drop down | Pass/Go
S2-5 | Email Deposit Services for Review | Email Deposit Services when Non-post = yes | Email was successfully sent with link that opens queue | Pass/Go
S2-6 | 4th MA: Review for Deposit Services | MA for Deposit Services to view SP info, add comments, and approve/deny release | Comment has been added and release denied | Pass/Go
S2-7 | Email Requestor of Incomplete Release | Email Requestor if Deposit Services deny the release | Email was successfully sent with link that opens queue | Pass/Go
S2-8 | 5th MA: Review of SP Release (assigned to requestor) | Incomplete Release Review MA opens in queue to notifify requestor that SP release was denied | Incomplete Release Review MA was created in queue and | Pass/Go
S2-9 | Document Filed to Synergy | Document files successfully to synergy | Fields and Indexes succesfully filled | Pass/Go | Account was a savings account so it was placed in Stop Payments - SAV in synergy
S2-10 | Confirm that Stop was NOT released from account | Stop Payment should still be on the customers account | Stop Payment is still placed on customer account | Pass/Go
S2-11
S2-12
S2-13
S2-14
S2-15
S2-16
S2-17
S2-18
S2-19
S2-20
S2-21
S2-22
S2-23
S2-24
S2-25
S2-26
Scenario #3: | Release of Stop Payment: Non-post = no
Test Case #: | Test Scenario: | Expected Results: | Actual Results: | Status: | Notes:
S3-1 | Start Workflow from queue | First manual activity will auto open | First MA opened | Pass/Go
S3-2 | 1st MA: Enter Account Number | Enter account number to pull back customer information | Account number entered | Pass/Go | Account# 700310808
S3-3 | 2nd MA: Enter Stop Payment Info | Enter the stop payment info: Select Customer, How SP was requested, Date SP was placed, Amount, Present on Non-post. | The SP info was entered | Pass/Go
S3-4 | 3rd MA: Select Stop to Release | Select the desired stop payment from the drop down | The correct stop payment was in the drop down | Pass/Go
S3-5 | 4th MA: Confimation of SP Release | Confirmation MA opens in queue to notifify requestor that SP was released | Confirmation successful | Pass/Go
S3-6 | Document Filed to Synergy | Document files successfully to synergy | Fields and Indexes succesfully filled | Pass/Go | Account was a checking account so it was placed in Stop Payments - DDA in synergy
S3-7 | Confirm Stop was removed from customer account | Stop Payment should no longer be on customer account | Stop has been removed from account | Pass/Go
S3-8
S3-9
S3-10
S3-11
S3-12
S3-13
S3-14
S3-15
S3-16
S3-17
S3-18
S3-19
S3-20
S3-21
S3-22
S3-23
S3-24
S3-25
S3-26
Note on B5: Brandi Rose: Need to test various scenario's to ensure WorkFlow is working as intended. Please test happy and negative paths to cover all possible outcomes.
Note on B33: Brandi Rose: Need to test various scenario's to ensure WorkFlow is working as intended. Please test happy and negative paths to cover all possible outcomes.
Note on B65: Brandi Rose: Need to test various scenario's to ensure WorkFlow is working as intended. Please test happy and negative paths to cover all possible outcomes.

## WFA Screenshots
*Please include the Test Case # before each screenshot, this will assist with identifying and resolving issues.
S1-2
S1-3
S1-4
S1-5
S1-6
S1-7
S1-8
S1-9
S2-2
S2-3
S2-4
S2-5
S2-6
S2-7
(email has been updated to take out the big space between the text)
S2-8
S2-9
S2-10
S3-2
S3-3
S3-4
S3-5
S3-6
S3-7

## BA Testing
| WorkFlow Project: | Release of Stop Payment | Testing Date:
| Business Line Testing: | Business Analyst | Final Results:
| Test Plan Designed By: |  | Test Plan Executed By:
Scenario #1:
Test Case #: | Test Scenario: | Expected Results: | Actual Results: | Status: | Notes:
S1-1 | Open WF from Account # |  | WF Opened | Pass/Go | EXAMPLE
S1-2 | Account Look-up | All Account # will prefill into to WF for verification | Account info did not populate | Fail | EXAMPLE
S1-3 | Officer Approval | Route to Officer for Approval | Officer to approve no listed in drop down | On Hold | EXAMPLE
S1-1
S1-2
S1-3
S1-4
S1-5
S1-6
S1-7
S1-8
S1-9
S1-10
S1-11
S1-12
S1-13
S1-14
S1-15
S1-16
S1-17
S1-18
S1-19
S1-20
S1-21
S1-22
Scenario #2:
Test Case #: | Test Scenario: | Expected Results: | Actual Results: | Status: | Notes:
S2-1
S2-2
S2-3
S2-4
S2-5
S2-6
S2-7
S2-8
S2-9
S2-10
S2-11
S2-12
S2-13
S2-14
S2-15
S2-16
S2-17
S2-18
S2-19
S2-20
S2-21
S2-22
S2-23
S2-24
S2-25
S2-26
Scenario #3:
Test Case #: | Test Scenario: | Expected Results: | Actual Results: | Status: | Notes:
S3-1
S3-2
S3-3
S3-4
S3-5
S3-6
S3-7
S3-8
S3-9
S3-10
S3-11
S3-12
S3-13
S3-14
S3-15
S3-16
S3-17
S3-18
S3-19
S3-20
S3-21
S3-22
S3-23
S3-24
S3-25
S3-26
Note on B5: Brandi Rose: Need to test various scenario's to ensure WorkFlow is working as intended. Please test happy and negative paths to cover all possible outcomes.
Note on B36: Brandi Rose: Need to test various scenario's to ensure WorkFlow is working as intended. Please test happy and negative paths to cover all possible outcomes.
Note on B68: Brandi Rose: Need to test various scenario's to ensure WorkFlow is working as intended. Please test happy and negative paths to cover all possible outcomes.

## BA Screenshots
*Please include the Test Case # before each screenshot, this will assist with identifying and resolving issues.

## BL Testing
| WorkFlow Project: | Release of Stop Payment | Testing Date:
| Business Line Testing: |  | Final Results:
| Test Plan Designed By: |  | Test Plan Executed By:
Scenario #1:
Test Case #: | Test Scenario: | Expected Results: | Actual Results: | Status: | Notes:
S1-1 | Open WF from Account # |  | WF Opened | Pass/Go | EXAMPLE
S1-2 | Account Look-up | All Account # will prefill into to WF for verification | Account info did not populate | Fail | EXAMPLE
S1-3 | Officer Approval | Route to Officer for Approval | Officer to approve no listed in drop down | On Hold | EXAMPLE
S1-1
S1-2
S1-3
S1-4
S1-5
S1-6
S1-7
S1-8
S1-9
S1-10
S1-11
S1-12
S1-13
S1-14
S1-15
S1-16
S1-17
S1-18
S1-19
S1-20
S1-21
S1-22
Scenario #2: | Daily Print Adverse Action Manual Activity
Test Case #: | Test Scenario: | Expected Results: | Actual Results: | Status: | Notes:
S2-1
S2-2
S2-3
S2-4
S2-5
S2-6
S2-7
S2-8
S2-9
S2-10
S2-11
S2-12
S2-13
S2-14
S2-15
S2-16
S2-17
S2-18
S2-19
S2-20
S2-21
S2-22
S2-23
S2-24
S2-25
S2-26
Scenario #3:
Test Case #: | Test Scenario: | Expected Results: | Actual Results: | Status: | Notes:
S3-1
S3-2
S3-3
S3-4
S3-5
S3-6
S3-7
S3-8
S3-9
S3-10
S3-11
S3-12
S3-13
S3-14
S3-15
S3-16
S3-17
S3-18
S3-19
S3-20
S3-21
S3-22
S3-23
S3-24
S3-25
S3-26
Note on B5: Brandi Rose: Need to test various scenario's to ensure WorkFlow is working as intended. Please test happy and negative paths to cover all possible outcomes.
Note on B36: Brandi Rose: Need to test various scenario's to ensure WorkFlow is working as intended. Please test happy and negative paths to cover all possible outcomes.
Note on B68: Brandi Rose: Need to test various scenario's to ensure WorkFlow is working as intended. Please test happy and negative paths to cover all possible outcomes.

## BL Screenshots
*Please include the Test Case # before each screenshot, this will assist with identifying and resolving issues.

## BL #2 Testing
| WorkFlow Project: | Release of Stop Payment | Testing Date:
| Business Line Testing: |  | Final Results:
| Test Plan Designed By: |  | Test Plan Executed By:
Scenario #1:
Test Case #: | Test Scenario: | Expected Results: | Actual Results: | Status: | Notes:
S1-1 | Open WF from Account # |  | WF Opened | Pass/Go | EXAMPLE
S1-2 | Account Look-up | All Account # will prefill into to WF for verification | Account info did not populate | Fail | EXAMPLE
S1-3 | Officer Approval | Route to Officer for Approval | Officer to approve no listed in drop down | On Hold | EXAMPLE
S1-1
S1-2
S1-3
S1-4
S1-5
S1-6
S1-7
S1-8
S1-9
S1-10
S1-11
S1-12
S1-13
S1-14
S1-15
S1-16
S1-17
S1-18
S1-19
S1-20
S1-21
S1-22
Scenario #2:
Test Case #: | Test Scenario: | Expected Results: | Actual Results: | Status: | Notes:
S2-1
S2-2
S2-3
S2-4
S2-5
S2-6
S2-7
S2-8
S2-9
S2-10
S2-11
S2-12
S2-13
S2-14
S2-15
S2-16
S2-17
S2-18
S2-19
S2-20
S2-21
S2-22
S2-23
S2-24
S2-25
S2-26
Scenario #3:
Test Case #: | Test Scenario: | Expected Results: | Actual Results: | Status: | Notes:
S3-1
S3-2
S3-3
S3-4
S3-5
S3-6
S3-7
S3-8
S3-9
S3-10
S3-11
S3-12
S3-13
S3-14
S3-15
S3-16
S3-17
S3-18
S3-19
S3-20
S3-21
S3-22
S3-23
S3-24
S3-25
S3-26
Note on B5: Brandi Rose: Need to test various scenario's to ensure WorkFlow is working as intended. Please test happy and negative paths to cover all possible outcomes.
Note on B36: Brandi Rose: Need to test various scenario's to ensure WorkFlow is working as intended. Please test happy and negative paths to cover all possible outcomes.
Note on B68: Brandi Rose: Need to test various scenario's to ensure WorkFlow is working as intended. Please test happy and negative paths to cover all possible outcomes.

## BL #2 Screenshots
*Please include the Test Case # before each screenshot, this will assist with identifying and resolving issues.

## BL #3 Testing
| WorkFlow Project: | Release of Stop Payment | Testing Date:
| Business Line Testing: |  | Final Results:
| Test Plan Designed By: |  | Test Plan Executed By:
Scenario #1:
Test Case #: | Test Scenario: | Expected Results: | Actual Results: | Status: | Notes:
S1-1 | Open WF from Account # |  | WF Opened | Pass/Go | EXAMPLE
S1-2 | Account Look-up | All Account # will prefill into to WF for verification | Account info did not populate | Fail | EXAMPLE
S1-3 | Officer Approval | Route to Officer for Approval | Officer to approve no listed in drop down | On Hold | EXAMPLE
S1-1
S1-2
S1-3
S1-4
S1-5
S1-6
S1-7
S1-8
S1-9
S1-10
S1-11
S1-12
S1-13
S1-14
S1-15
S1-16
S1-17
S1-18
S1-19
S1-20
S1-21
S1-22
Scenario #2:
Test Case #: | Test Scenario: | Expected Results: | Actual Results: | Status: | Notes:
S2-1
S2-2
S2-3
S2-4
S2-5
S2-6
S2-7
S2-8
S2-9
S2-10
S2-11
S2-12
S2-13
S2-14
S2-15
S2-16
S2-17
S2-18
S2-19
S2-20
S2-21
S2-22
S2-23
S2-24
S2-25
S2-26
Scenario #3:
Test Case #: | Test Scenario: | Expected Results: | Actual Results: | Status: | Notes:
S3-1
S3-2
S3-3
S3-4
S3-5
S3-6
S3-7
S3-8
S3-9
S3-10
S3-11
S3-12
S3-13
S3-14
S3-15
S3-16
S3-17
S3-18
S3-19
S3-20
S3-21
S3-22
S3-23
S3-24
S3-25
S3-26
Note on B5: Brandi Rose: Need to test various scenario's to ensure WorkFlow is working as intended. Please test happy and negative paths to cover all possible outcomes.
Note on B36: Brandi Rose: Need to test various scenario's to ensure WorkFlow is working as intended. Please test happy and negative paths to cover all possible outcomes.
Note on B68: Brandi Rose: Need to test various scenario's to ensure WorkFlow is working as intended. Please test happy and negative paths to cover all possible outcomes.

## BL #3 Screenshots
*Please include the Test Case # before each screenshot, this will assist with identifying and resolving issues.